## Document_Cover_Sheet
Rabbit Finance
Created By | Ramsahay
Date | 2021-06-08
Summary Report
| Critical | Major | Minor | ENH | Total
New | 1 | 3 | 3 | 1 | 8
=
=
=
=

## BUG
S No. | # | Type | Status | Summary | Steps | Issue | Remarks
1 | Bug#1 | Minor | NEW | Personal Insurance --> Personal information--> DOB : year accepting '00' | 1. Navigate to the website. 2. Chose 'Insurance Type and Sub-Type 3. Enter user information 4. Enter DOB as '00' | 1. DOB should not accept the DOB as '00', it should always take YYYY and not less than 1900 | please refer screen shot "DOB"
2 | Bug#2 | Major | NEW | Personal Insurance --> enter all details ---> Chose insurance plan --> Chose nationality --> enter passport no --> NEXT --> Delete again the passport no : user still continue and showing the error for the passport no field | 1. Navigate to the website. 2. Chose 'Insurance Type and Sub-Type 3. Enter user information 4. chose Insurance plan 5. enter user information --> NEXT 6. delete previous user details | 1. User should not be able to go to the next step i.e. payment page. before moving on next step, system should show error message Suggestions: Previous information fields should be disable and have some option to edit previous information. | please refer screen shot "Passport"
3 | Bug#3 | Minor | NEW | Personal Insurance --> enter all details ---> Chose insurance plan --> buy the plan --> order summary page --> Browser back button : on the Insurance page , still showing progress bar on last section i.e. "Quotes" | 1. Navigate to the website. 2. Chose 'Insurance Type and Sub-Type 3. Enter user information 4. chose Insurance plan 5. Buy insurance 6. click on browser back button. | 1. After Buying the insurance, when user click on browser back button, still progress bar on last steps section i.e. Quotes. | please refer screen shot
4 | Bug#4 | Critical | NEW | Personal Insurance --> enter all details ---> Chose insurance plan --> buy the plan without acknowledge personal information : still user able to purchase the insurance but should not be able to purchase. | 1. Navigate to the website. 2. Chose 'Insurance Type and Sub-Type 3. Enter user information 4. without acknowledge personal information 5. chose Insurance plan 6. Buy insurance | 1. user able to purchase the plan but without acknowledge personal information things user should not be able to purchase the insurance | please refer screen shot "4"
5 | Bug#5 | Major | NEW | Personal Insurance --> enter all details ---> Chose insurance plan --> buy the plan : there is no validation when user try to buy the insurance without accepting "I hereby confirm that:" | 1. Navigate to the website. 2. Chose 'Insurance Type and Sub-Type 3. Enter user information 4. chose Insurance plan 5. Deselect all "I hereby confirm that:" agreement and click on NEXT 6. user can see the order summary section (before payment) 7. again user select some check box "I hereby confirm that:" | 1. Confirm and Buy button showing before showing the prder summary section , if user not selecting the "I hereby confirm that:" things , system should show the error. | please refer screen shot "5"
6 | Bug#6 | Major | NEW | Personal Insurance --> enter all details ---> click on Quote : some time cookies is not working | 1. Navigate to the website. 2. Chose 'Insurance Type and Sub-Type 3. Enter user information 4. click on Quote button | 1. web cookies is not working and no proper message is showing so that user can understand what is wrong with system,. | Refer the video "Confirm" and "Cookies"
7 | ENH#1 | ENH | NEW | Personal Insurance --> enter all details ---> Buy insurance --> Payment gateway page : need to improve the error message | 1. Navigate to the website. 2. Chose 'Insurance Type and Sub-Type 3. Enter user information 4. Chose insurance --> payment gateway page 5. Credit card section | 1. For card expiry --> error message should be shown like "Expiry month and year both are required" | please refer screen shot "6"
8 | Bug#7 | Minor |  | Personal Insurance --> enter all details ---> Quote page : filter default values is not updated. | 1. Navigate to the website. 2. Chose 'Insurance Type and Sub-Type 3. Enter user informationm--> on Insurance Quote plan page --> On page page, filetr showing according user select from intial steps. 4. change the URL https://staging-finance.rabbitinternet.com/en/product/health-insurance/quotes ==> https://staging-finance.rabbitinternet.com/en/product/health-insurance/questions 5. Chose different insurnace type and NEXT | 1. On Quote page ,Filter not updated based on the updated insurance type and sub type. | please refer screen shot "7"
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Bug Replication steps.
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Remarks if required.